## 1. Product Overview
Item | Description
Product Name | Patient Monitoring System
Product Vision/ Purpose | To provide real-time monitoring of patients' vital signs and health data using IoT-enabled sensors and a secure digital dashboard, allowing healthcare professionals to make timely decisions and reduce response time during emergencies.
Business Goals / Key Success factors | - Enable continuous and remote patient monitoring - Reduce hospital workload through automation and data visualization - Ensure data accuracy and patient safety through secure storage and alert mechanisms - Improve patient outcomes through proactive medical intervention
Primary Stakeholders | Primary stakeholders include doctors, nurses, hospital administrators, technical development team, and patients who will be monitored using the system.

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E1 | User Authentication | US1 | As a user, I want to sign up securely using email and OTP for verified access. | Frontend authentication integrated with backend API and OTP service | Must Have | 8 | Done | Frontend Dev Team | Validate user authentication and OTP flow | QA Lead
E2 | Patient Data Management | US2 | As a doctor, I want to view and update patient details efficiently for personalized care. | Database schema for patient details and record management | Must Have | 10 | In Progress | Backend Dev Team | Verify data CRUD operations for patients | QA Team
E3 | Real-Time Monitoring Dashboard | US3 | As a nurse, I want a dashboard displaying real-time vitals and patient status. | Dynamic dashboard frontend using React/HTML/CSS with live data rendering | Must Have | 13 | In Progress | Frontend + Backend | Check real-time data updates and visual accuracy | QA Team
E4 | Alert and Notification System | US4 | As a healthcare provider, I want instant alerts when abnormalities are detected in patient vitals. | Integration of alert logic via backend triggers and notification APIs | Should Have | 8 | Planned | Backend Team | Simulate abnormal readings to test alert triggers | QA Team
E5 | Reports & Analytics | US5 | As an admin, I want to generate downloadable reports and health analytics summaries. | Backend logic for report generation and chart visualization | Could Have | 5 | Planned | Full Stack Team | Ensure correct report generation and data export | QA Lead

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
v0.1 | 2025-11-15 | Frontend Authentication Module and UI completion | UI design finalized | Completed
v0.2 | 2025-11-22 | Backend APIs for patient data and dashboard integration | Requires database connection setup | In Progress
v0.3 | 2025-11-29 | Real-time data visualization and alert mechanisms | Depends on API and sensor integration | Planned
v0.4 | 2025-12-06 | System testing, bug fixes, and final deployment | Depends on all modules being stable | Planned

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Frontend development completed successfully with clean UI and responsive design. | Minor delays in backend setup due to API connection issues. | Enhance backend documentation and fix API integration issues. | Backend Team
Team collaboration and task distribution were efficient. | Limited testing environment slowed progress. | Set up a stable testing environment early in the sprint. | Testing Team
Project vision and feature requirements are clearly defined. | Initial confusion around database schema design. | Conduct weekly sync meetings to ensure alignment. | Project Lead